## Digital pharmacy checklist
Draft template
| Topic: | Draft checklist to support digital pharmacy changes: <topic title here>
Task ID ref |  | Next step / action / task /sub-task (some cells can be clicked to learn more background about the task) | Goal or success criteria | Category | Status next steps, resources required, outcomes? (enter N/A if need) | Persons owning? | Timings / deadline | Extra tasks added? (y/n) | RAG | Done? (use dropdown)
1 |  | Early discussion: NHSE TD are briefed on the change or change options, so NHSE TD [and/or NHSBSA] can begin discussion with IT suppliers. | Initially assessed | Initiation |  |  |  |  | Clear
2 |  | Implementation sub-group feed in: to assist NHSE TD and suppliers with digital planning and implementation. | Implementation sub-group to feed into plans | Initiation |  |  |  |  | Clear
3 |  | Define change: The change is explained within a shared written document for IT suppliers (it will iterate over time.) | Change defined | Initiation |  |  |  |  | Clear
4 |  | Assign priority: Change required has priority attached, and wider priority sequencing is considered. | Change prioritised | Initiation |  |  |  |  | Clear
5 |  | Initial feasibility discussion: Initial NHSE TD discussion with IT suppliers regarding feasibility for change/options. | Initially assessed | Initiation |  |  |  |  | Clear
6 |  | Draft technical instructions: Technical instructions drafted. | Tech instructions prepped | Preparation |  |  |  |  | Clear
7 |  | Share drafted technical instructions (to suppliers and the implementation group for comment). | Tech instructions to suppers for comment | Preparation |  |  |  |  | Clear
8 |  | Supplier and the implementation group comment: on the drafted technical instructions. | Suppliers commented on instructions | Preparation |  |  |  |  | Clear
9 |  | Update draft instructions (taking into account of those comments that are accepted) | Tech instructions amended? | Preparation |  |  |  |  | Clear
10 |  | Collate supplier views: NHSE TD collation of supplier views regarding deeper discovery. | Suppliers considered impacts | Preparation |  |  |  |  | Clear
11 |  | Further estimate scope and level of supplier work required: Via NHSE TD talks with suppliers. | Suppliers provided views on work needed? | Preparation |  |  |  |  | Clear
12 |  | Consider IT solution diversity and NHS DSIC: will multiple systems (minimum 3+, ideally more) implement the change. | Considered solution diversity | Preparation |  |  |  |  | Clear
13 |  | Referrals: Check whether changes to referral mechanisms are needed? Are further related sub-tasks needed? | Checked whether referrals work needed | Preparation |  |  |  |  | Clear
14 |  | Pharmacy data entry: Determine whether pharmacy data entry process changes are needed? | Determined data entry impacts & MYS API | Preparation |  |  |  |  | Clear
15 |  | Submission: Assess whether pharmacy submission changes are needed? | Assessed pharmacy submission factors | Preparation
16 |  | Schedule of Payment: Plan if pharmacy Schedule of Payment changes are needed? | Planned for Schedule of Payment factors | Preparation
17 |  | Regulations: Consider whether Regulatory changes are needed? | Considered whether regs factors impact IT | Preparation
18 |  | Drug Tariff: Plan towards later Drug Tariff changes if these are needed? | Planned whether DT factors impact IT | Preparation
19 |  | Health records: Consider Electronic Health Records impact? | Considered data entry impacts | Refining |  |  |  |  | Clear
20 |  | Paperless: Take into account of paperless pharmacy processing opportunities? | Taken into account data entry impacts | Refining |  |  |  |  | Clear
21 |  | DoS/NHS website: If applicable, assess how the change impacts DoS, NHS website, or NHS Profile Manager. | Assessed profiles impacts | Refining |  |  |  |  | Clear
22 |  | Plan for patient service visibility: If applicable, assess how the change impacts patients' sight of the service | Planned serv navigation impacts | Refining |  |  |  |  | Clear
23 |  | Post-event messages: Evaluate whether post-event messages require change? | Evaluated post event mssgs impacts | Refining |  |  |  |  | Clear
24 |  | Patient notifications: If applicable, consider how patient notifications are impacted | Assessed patient messages impacts | Refining |  |  |  |  | Clear
25 |  | Guidance: Plan towards later guidance updates | Assessed guidance needed | Refining |  |  |  |  | Clear
26 |  | IT contingencies: Assess IT contingency plans for suppliers and pharmacies. | Assessed towards contingencies | Refining |  |  |  |  | Clear
27 |  | Sign-in impacts: Take into account of opportunities for easier sign-up/login. | Taken into account if sign-up impacts | Refining |  |  |  |  | Clear
28 |  | Plan towards supplier pre-launch testing: Supplier pre-launch testing is scheduled and planned | Planned towards supplier testing | Pre-rollout
29 |  | NHSE TD pre-launch testing is planned in: NHSE TD pre-launch testing. | Planned towards NHSE TD testing | Pre-rollout
30 |  | Schedule checkpoints: Go/no-go checkpoint dates are scheduled (these can be tweaked later if needed). | Scheduled go-no-go checkpoints | Pre-rollout |  |  |  |  | Clear
31 |  | Penultimate checkpoint scheduled: Penultimate go/no-go has launch date approved or re-scheduled. | Scheduled penultimate go-no-go checkpoints | Rollout
32 |  | Initial launch occurs: Initial launch occurs (even if within a staggered fashion, e.g., some suppliers/some pharmacies). | Launch ocurred | Rollout
33 |  | Supplier rollout observations: Observation of early rollout by suppliers. | Early observations by suppliers | Rollout
34 |  | NHSE TD rollout observations: Observation of early rollout by NHSE TD. | Early observations by NHSE TD | Rollout
35 |  | Full rollout is reached: Full rollout has occurred. | Full rolout occurred | Rollout
36 |  | Pricing spot checks: Earlier pharmacy reimbursement checks suggest scenarios are priced as expected. | Pricing spot checks carried out | Rollout
37 |  | Additional task example 1: Further tasks and sub-tasks can be added, as required to this excel task checklist | <tbc for each further sub-task added> | Various |  |  |  |  | Clear
38 |  | Additional tasks example 2: Further tasks and sub-tasks can be added, as required to this excel task checklist | <tbc for each further sub-task added> | Various |  |  |  |  | Clear
#

## Notes
The purpose of this draft factsheet is for relevant organisations to consider whether it can assist with consideration of NHS pharmacy policy best impacting NHS pharmacy IT solutions available for community pharmacies
This template is in development and to comment contact: daniel.ah-thion@cpe.org.uk
The template takes into account past feedback from CP ITG supplie and pharmacy representatives regarding common and useful implmentation steps

## TaskStatus (hidden)
List of task statuses used for 'Done' column dropdown box
Not started
In progress
Waiting
Partially done
Completed
Not required or N/A